## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BASUDEBPUR Piped Water Supply Scheme | SM/14182 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Lahutara, 2. Hemenpur, 3. Basudebpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000295/2022-2023 | 541/RD/PHE | 22/02/2023 | 08/04/2023 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 61.71 | 0 | 0 | 60
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BASUDEBPUR Piped Water Supply Scheme | SM/14182 | New | Implementation of BASUDEBPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000324/2022-2023 | 562/RD/PHE | 23/02/2023 | 24/12/2025 | M/S LOKENATH CONSTRUCTION | 536.97 | 208.66 | 38.86 | 45
3 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BASUDEBPUR Piped Water Supply Scheme | SM/14182 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Basudebpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017263) | Assistant Engineer - I | Junior Engineer-02 | ORD/000419/2023-2024 | 2470/MLMD | 04/08/2023 | 24/09/2026 | ANIMA ENTERPRISE | 25.54 | 0.98 | 3.82 | 76
4 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BASUDEBPUR Piped Water Supply Scheme | SM/14182 | New | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 1199/RD/PHE | 28/04/2023 | 28/04/2023 | Resource Division | 54.77 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BASUDEBPUR Piped Water Supply Scheme | SM/14182 | New | Construction of concrete pathway with earth filling at Head Work Site Pump House & 2nd TW Site Pump House for Basudebpur Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHE Dte.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000349/2024-2025 | 3302/RD/PHE | 20/11/2024 | 20/12/2024 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 10.41 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BASUDEBPUR Piped Water Supply Scheme | SM/14182 | New | Additional pipeline and other ancillary works at Basudebpur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000348/2024-2025 | 3301/RD/PHE | 20/11/2024 | 04/01/2025 | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. | 36.59 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BASUDEBPUR Piped Water Supply Scheme | SM/14182 | New | Quotation for new service connection at BASUDEBPUR PH-I (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/14182). |  |  | BILL/02748/2024-2025 | BP-2024-25-610 | 06/02/2025 | 06/02/2025 | W.B.S.E.D.C.LTD | 4.09 | 0 | 0 | 0
Total | [13 empty] | 730.08 | 209.64 | 28.71