## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Barobilla Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14225 | Augmentation | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Barobilla Piped Water Supply Scheme of Chopra Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000188/2022-2023 | 56/RD/PHE | 16/01/2023 | 02/03/2023 | SUSANTA GOBINDA DEB GOPALDEB9475@GMAIL.COM | 28.53 | 0 | 0 | 60
2 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Barobilla Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14225 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Barabilla Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016481) | Assistant Engineer - I | Junior Engineer-02 | ORD/001806/2023-2024 | 3693/MLMD | 29/11/2023 | 27/07/2026 | DAS CONSTRUCTION | 10.91 | 9.18 | 84.17 | 84
3 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Barobilla Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14225 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 2388/RD/PHE | 17/08/2023 | 17/08/2023 | Resource Division | 2.4 | 0 | 0 | 0
Total | [13 empty] | 41.84 | 9.18 | 21.95