## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Pokheria Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14226 | Augmentation | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Pokheria Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000194/2022-2023 | 62/RD/PHE | 16/01/2023 | 14/08/2025 | RAHUL ENTERPRISE RNJRAHULENTERPRISE@GMAIL.COM | 17.78 | 9.1 | 51.17 | 90
2 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Pokheria Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14226 | Augmentation | Rig Bored Tube-Well in connection with Source Augmentation In Different Piped Water Supply Scheme 1.Mohua, 2. Pawakhali, 3. Pokheria in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000278/2022-2023 | 471/RD/PHE | 16/02/2023 | 02/04/2023 | M/S SARKAR ENTERPRISE SILIGURI | 31.92 | 0 | 0 | 80
3 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Pokheria Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14226 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Pokheria Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016497) | Assistant Engineer - I | Junior Engineer-02 | ORD/002033/2023-2024 | 4771/MLMD | 29/12/2023 | 16/04/2025 | ARATI ENGINEERING | 10.91 | 0 | 0 | 100
4 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Pokheria Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14226 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 2399/RD/PHE | 17/08/2023 | 17/08/2023 | Resource Division | 2.38 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Pokheria Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14226 | Augmentation | Quotation for new service connection at Source Augmentation of POKHERIA PH-III (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00228/2024-2025 | BP-2024-25-79 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 14.28 | 0 | 0 | 0
Total | [13 empty] | 77.27 | 9.1 | 11.78