## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Siripur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14227 | Augmentation | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Siripur Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000195/2022-2023 | 63/RD/PHE | 16/01/2023 | 02/03/2023 | M/S DOLPHIN CONSTRUCTION DOLPHIN.RGJ@GMAIL.COM | 17.7 | 0 | 0 | 60
2 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Siripur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14227 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Siripur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016479) | Assistant Engineer - I | Junior Engineer-02 | ORD/000543/2023-2024 | 2533/MLMD | 04/08/2023 | 02/12/2023 | BASUDEV GHOSH. | 10.91 | 8.57 | 78.53 | 79
3 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Siripur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14227 | Augmentation | Rig Bored Tube-Well In connection with Source Augmentation In Different Piped Water Supply Scheme 1.Debiganj, 2.Gunabari, 3. Majlishpur. 4. Sripur in the District of Uttar Dinajpur Under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000277/2022-2023 | 470/RD/PHE | 16/02/2023 | 02/04/2023 | M/S SARKAR ENTERPRISE SILIGURI | 42.57 | 10.62 | 24.96 | 100
4 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Siripur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14227 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2023-2024 | 2400/RD/PHE | 17/08/2023 | 17/08/2023 | Resource Division | 2.4 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Siripur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14227 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Siripur, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02499/2023-2024 | BP-2023-24-435 | 04/01/2024 | 04/01/2024 | W.B.S.E.D.C.LTD | 4.79 | 0 | 0 | 0
Total | [13 empty] | 78.36 | 19.19 | 24.49