## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Gunabari Piped Water Suppply Scheme under Islampur block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14228 | Augmentation | Rig Bored Tube-Well In connection with Source Augmentation In Different Piped Water Supply Scheme 1.Debiganj, 2.Gunabari, 3. Majlishpur. 4. Sripur in the District of Uttar Dinajpur Under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000277/2022-2023 | 470/RD/PHE | 16/02/2023 | 02/04/2023 | M/S SARKAR ENTERPRISE SILIGURI | 42.57 | 0 | 0 | 100
2 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Gunabari Piped Water Suppply Scheme under Islampur block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14228 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Gunabari, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001942/2023-2024 | 4003268843 | 10/11/2023 | 08/02/2024 | W.B.S.E.D.C.LTD | 4.53 | 0 | 0 | 100
3 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Gunabari Piped Water Suppply Scheme under Islampur block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14228 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000101/2023-2024 | 2394/RD/PHE | 17/08/2023 | 17/08/2023 | Resource Division | 2.4 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Gunabari Piped Water Suppply Scheme under Islampur block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14228 | Augmentation | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Gunabari Piped Water Supply Scheme of Islampur Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000190/2022-2023 | 58/RD/PHE | 16/01/2023 | 31/07/2024 | JEET CONSTRUCTION UKILPARA CTNJIT38@GMAIL.COM | 17.58 | 0 | 0 | 100
5 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Gunabari Piped Water Suppply Scheme under Islampur block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14228 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Gunabari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016494) | Assistant Engineer - I | Junior Engineer-02 | ORD/000553/2023-2024 | 2504/MLMD | 04/08/2023 | 29/07/2024 | BASUDEV GHOSH. | 10.9 | 0 | 0 | 100
Total | [13 empty] | 77.99 | 0 | 0