## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Debiganj Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14229 | Augmentation | Rig Bored Tube-Well In connection with Source Augmentation In Different Piped Water Supply Scheme 1.Debiganj, 2.Gunabari, 3. Majlishpur. 4. Sripur in the District of Uttar Dinajpur Under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000277/2022-2023 | 470/RD/PHE | 16/02/2023 | 02/04/2023 | M/S SARKAR ENTERPRISE SILIGURI | 42.57 | 9.66 | 22.69 | 100
2 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Debiganj Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14229 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 2397/RD/PHE | 17/08/2023 | 17/08/2023 | Resource Division | 2.4 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Debiganj Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14229 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Debiganj Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016478) | Assistant Engineer - I | Junior Engineer-02 | ORD/000475/2023-2024 | 2485/MLMD | 04/08/2023 | 02/12/2023 | S.G.ENTERPRISE | 10.89 | 9.14 | 83.9 | 84
4 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Debiganj Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14229 | Augmentation | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Debiganj Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000189/2022-2023 | 57/RD/PHE | 16/01/2023 | 02/03/2023 | SUBHASIS MAJUMDER SUBHASIS@REDIFFMAIL.COM | 17.69 | 17.2 | 97.25 | 98
5 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Debiganj Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14229 | Augmentation | Land development at 3rd Pump House (Source Augmentation) site for Debiganj Piped Water Supply Scheme under Islampur Sub-Division under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000041/2024-2025 | 1701/RD/PHE | 10/06/2024 | 10/07/2024 | HAQUE CONSTRUCTION | 1.5 | 0.4 | 26.37 | 100
Total | [13 empty] | 75.05 | 36.4 | 48.5