## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Mahua Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14232 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 2395/RD/PHE | 17/08/2023 | 17/08/2023 | Resource Division | 2.4 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Mahua Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14232 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Mahua Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016477) | Assistant Engineer - I | Junior Engineer-02 | ORD/000526/2023-2024 | 2522/MLMD | 04/08/2023 | 02/12/2023 | JIBU SINGHA | 10.9 | 9.15 | 83.9 | 84
3 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Mahua Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14232 | Augmentation | Quotation for new service connection at Source Augmentation of MAHUA PH-III (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/14232) |  |  | BILL/02477/2024-2025 | BP-2024-25-569 | 14/11/2024 | 14/11/2024 | W.B.S.E.D.C.LTD | 6.89 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Mahua Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14232 | Augmentation | Rig Bored Tube-Well in connection with Source Augmentation In Different Piped Water Supply Scheme 1.Mohua, 2. Pawakhali, 3. Pokheria in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000278/2022-2023 | 471/RD/PHE | 16/02/2023 | 02/04/2023 | M/S SARKAR ENTERPRISE SILIGURI | 31.92 | 10.54 | 33.02 | 80
5 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Mahua Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | SM/14232 | Augmentation | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Mahua Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer, RWS | ORD/000191/2022-2023 | 59/RD/PHE | 16/01/2023 | 19/05/2025 | SUDIP MITRA SUDIP.RNJ@GMAIL.COM | 17.67 | 11.08 | 62.69 | 100
Total | [13 empty] | 69.8 | 30.77 | 44.08