## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | MIRJADPUR Piped Water Supply Scheme | SM/14627 | New | Material Requisition To Resource Division |  |  | RTOR000162/2022-2023 | 900/RD/PHE | 28/03/2023 | 28/03/2023 | Resource Division | 40.24 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | MIRJADPUR Piped Water Supply Scheme | SM/14627 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Mirjadpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016582) | Assistant Engineer - I | Junior Engineer-02 | ORD/000427/2023-2024 | 2447/MLMD | 04/08/2023 | 27/05/2026 | DILIP MAHATO. | 27.46 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | MIRJADPUR Piped Water Supply Scheme | SM/14627 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 26/08/2026 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
4 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | MIRJADPUR Piped Water Supply Scheme | SM/14627 | New | Additional pipeline, Pathway, Land development and other ancillary works at Mirjadpur piped water Supply Scheme Under Islampur Sub-Division under Raiganj Division, P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000366/2025-2026 | 2256/RD/PHE | 05/08/2025 | 03/12/2025 | S M CONSTRUCTION RAJ.GSHOSH325@GMAIL.COM | 55.93 | 0 | 0 | 0
Total | [13 empty] | 13054.7 | 0 | 0