## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | Dhamdhol Piped Water Supply Scheme. | SM/14639 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer RSD |  | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 04/10/2022 | RADIANT | 47.87 | 0 | 0 | 100
2 | UTTAR DINAJPUR | Itahar | Raiganj Division | Dhamdhol Piped Water Supply Scheme. | SM/14639 | New | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 2232/RD/PHE | 01/08/2023 | 01/08/2023 | Resource Division | 29.61 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Itahar | Raiganj Division | Dhamdhol Piped Water Supply Scheme. | SM/14639 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 03.06.2024 to 07.06.2024. |  |  | BILL/00130/2024-2025 | BP-2024-25-92 | 28/06/2024 | 28/06/2024 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Dhamdhol Piped Water Supply Scheme. | SM/14639 | New | Quotation for new service connection at DHAMDHOL PH-II (Itahar ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/03791/2023-2024 | BP-2024-25-16 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 6.04 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Dhamdhol Piped Water Supply Scheme. | SM/14639 | New | Quotation for new service connection at Dhamdhol PH-I (Itahar ccc) |  |  | BILL/03519/2023-2024 | BP-2023-24-539 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 3.97 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Itahar | Raiganj Division | Dhamdhol Piped Water Supply Scheme. | SM/14639 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period for 02.05.2024 to 03.05.2024, 06.05.2024 to 07.05.2024 and 09.05.2024 to 10.05.2024. |  |  | BILL/00131/2024-2025 | BP-2024-25-91 | 28/06/2024 | 28/06/2024 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Itahar | Raiganj Division | Dhamdhol Piped Water Supply Scheme. | SM/14639 | New | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS |  |  | BILL/01217/2023-2024 | BP-2024-25-25 | 24/04/2024 | 24/04/2024 | EXECUTIVE ENGINEER PWD ROADS | 6.55 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Itahar | Raiganj Division | Dhamdhol Piped Water Supply Scheme. | SM/14639 | New | Implementation of DHAMDOL and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under RaiganjDivision, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000311/2022-2023 | 565/RD/PHE | 23/02/2023 | 22/08/2025 | M/S LOKENATH CONSTRUCTION | 300.71 | 0 | 0 | 40
9 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Dhamdhol Piped Water Supply Scheme. | SM/14639 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no- I,II & Making compound yard lighting arrangement at T/W no- I of DHAMDHOL Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte (TSM/016124) | Assistant Engineer - I | Junior Engineer-02 | ORD/001834/2023-2024 | 3632/MLMD | 23/11/2023 | 28/03/2026 | DILIP MAHATO. | 25.51 | 0 | 0 | 83
10 | UTTAR DINAJPUR | Itahar | Raiganj Division | Dhamdhol Piped Water Supply Scheme. | SM/14639 | New | Construction Of Approach Road, Laying of Pipe Line And Other Allied Works Of Dhamdhol PWSS Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000391/2024-2025 | 3561/RD/PHE | 05/12/2024 | 02/09/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 71.06 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Itahar | Raiganj Division | Dhamdhol Piped Water Supply Scheme. | SM/14639 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12 months (Period from 17.10.2023 to 16.10.2024) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000627/2023-2024 | 2876/RD/PHE | 17/10/2023 | 17/10/2024 | ARNAB DUTTA | 4.8 | 0 | 0 | 100
12 | UTTAR DINAJPUR | Itahar | Raiganj Division | Dhamdhol Piped Water Supply Scheme. | SM/14639 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dhamdol Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 35 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000311/2025-2026 | 2476/RD/PHE | 12/09/2025 | 11/03/2026 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 18.01 | 0 | 0 | 0
Total | [13 empty] | 514.32 | 0 | 0