## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | Gorahar Piped Water Supply Scheme. | SM/14640 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer RSD |  | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 04/10/2022 | RADIANT | 47.87 | 3.6 | 7.52 | 100
2 | UTTAR DINAJPUR | Itahar | Raiganj Division | Gorahar Piped Water Supply Scheme. | SM/14640 | New | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 2230/RD/PHE | 01/08/2023 | 01/08/2023 | Resource Division | 24.45 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Itahar | Raiganj Division | Gorahar Piped Water Supply Scheme. | SM/14640 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under GORAHAR PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000493/2023-2024 | 613/RD/PHE | 05/03/2024 | 19/04/2024 | M/S NATARAJ CONSTRUCTION DEBUABCD.1234@REDIFFMAIL.COM | 22.58 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Gorahar Piped Water Supply Scheme. | SM/14640 | New | Quotation for new service connection at GORAHAR PH-I (Itahar ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/03740/2023-2024 | BP-2023-24-691 | 15/03/2024 | 15/03/2024 | W.B.S.E.D.C.LTD | 5.55 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Gorahar Piped Water Supply Scheme. | SM/14640 | New | Quotation for new service connection at GORAHAR PH-II (Birnagar ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/03741/2023-2024 | BP-2023-24-692 | 15/03/2024 | 15/03/2024 | W.B.S.E.D.C.LTD | 5.89 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Gorahar Piped Water Supply Scheme. | SM/14640 | New | Additional Quotation for new service connection at GORAHAR PH-I (ITAHAR ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/14640) |  |  | BILL/02078/2024-2025 | BP-2024-25-484 | 09/09/2024 | 09/09/2024 | W.B.S.E.D.C.LTD | 3.44 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Gorahar Piped Water Supply Scheme. | SM/14640 | New | Additional Quotation for TW No- II of Gorahar Water supply scheme, Birnagar CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/01597/2024-2025 | BP-2024-25-398 | 29/07/2024 | 29/07/2024 | W.B.S.E.D.C.LTD | 2.39 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Itahar | Raiganj Division | Gorahar Piped Water Supply Scheme. | SM/14640 | New | Implementation of GORAHAR and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000315/2022-2023 | 564/RD/PHE | 23/02/2023 | 31/12/2025 | SANYAL ENTERPRISE | 243.13 | 104.94 | 43.16 | 38
9 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Gorahar Piped Water Supply Scheme. | SM/14640 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no- I,II & Making compound yard lighting arrangement at T/W no- I of GORAHAR Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016130) | Assistant Engineer - I | Junior Engineer-02 | ORD/001697/2023-2024 | 3422/MLMD | 01/11/2023 | 21/10/2025 | MAA BHABOTARINE ENTERPRISE | 25.16 | 18.5 | 73.5 | 78
10 | UTTAR DINAJPUR | Itahar | Raiganj Division | Gorahar Piped Water Supply Scheme. | SM/14640 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Gorahar PWSS at Itahar Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000478/2024-2025 | 11/RD/PHE | 02/01/2025 | 16/02/2025 | AJIT PRAMANIK | 29.8 | 0 | 0 | 0
Total | [13 empty] | 410.27 | 127.03 | 30.96