## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14641 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer RSD |  | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 04/10/2022 | RADIANT | 47.87 | 5.28 | 11.03 | 100
2 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14641 | New | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 2231/RD/PHE | 01/08/2023 | 01/08/2023 | Resource Division | 40.65 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14641 | New | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under CHANDIGRAM PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000499/2023-2024 | 622/RD/PHE | 05/03/2024 | 15/12/2024 | MITALI CONSTRUCTION | 24.47 | 10.98 | 44.88 | 60
4 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14641 | New | Quotation for new service connection at Chandigram PH-I (Itahar ccc) |  |  | BILL/03516/2023-2024 | BP-2023-24-536 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 3.63 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14641 | New | Implementation of CHANDIGRAM and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000317/2022-2023 | 568/RD/PHE | 23/02/2023 | 22/08/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 381.9 | 146.43 | 38.34 | 40
6 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14641 | New | Construction of Approach Road,Laying of Pipe Line,Fhtc And other Allied Works of Chandigram Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000392/2024-2025 | 3562/RD/PHE | 05/12/2024 | 06/03/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 80.89 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14641 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Chandigram Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 50 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000269/2025-2026 | 1657/RD/PHE | 23/06/2025 | 20/12/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 20.73 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14641 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 11/04/2024 | HORIZEN | 5 | 0.04 | 0.82 | 100
9 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14641 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no- I,II & Making compound yard lighting arrangement at T/W no- I of CHANDIGRAM Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016709) | Assistant Engineer - I | Junior Engineer-02 | ORD/000738/2023-2024 | 2799/MLMD | 17/08/2023 | 13/02/2024 | SHREE BISHNU CONSTRUCTION | 25.79 | 19.81 | 76.82 | 77
10 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14641 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59C 0644) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 01/07/2024 to 14/01/2025. | Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RWS | ORD/000407/2024-2025 | 1980/RD/PHE | 29/06/2024 | 13/01/2025 | PRITAM SARKAR | 2.6 | 0.4 | 15.37 | 100
11 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14641 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Sheme in different Block in the District of Uttar Dinajpur under Raiganj Division,PHE Dte.. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000518/2024-2025 | 58/RD/PHE | 03/01/2025 | 12/02/2026 | TECHVISION | 5 | 0 | 0 | 83
Total | [13 empty] | 638.51 | 182.95 | 28.65