## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14642 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer RSD |  | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 04/10/2022 | RADIANT | 47.87 | 5.06 | 10.58 | 100
2 | UTTAR DINAJPUR | Itahar | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14642 | New | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 2251/RD/PHE | 03/08/2023 | 03/08/2023 | Resource Division | 38.67 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14642 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no- I,II & Making compound yard lighting arrangement at T/W no- I of BASRATPUR Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016824) | Assistant Engineer - I | Junior Engineer-02 | ORD/000402/2023-2024 | 2438/MLMD | 04/08/2023 | 27/05/2026 | HANNAN BUILDERS PVT. LTD. | 25.52 | 18.4 | 72.08 | 72
4 | UTTAR DINAJPUR | Itahar | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14642 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 20.05.2024 to 22.05.2024 and 24.05.2024. |  |  | BILL/00132/2024-2025 | BP-2024-25-95 | 28/06/2024 | 28/06/2024 | M/S DILWAR HOSAIN | 0.07 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14642 | New | Quotation for new service connection at BASRATPUR PH-I (Itahar ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/03742/2023-2024 | BP-2023-24-690 | 15/03/2024 | 15/03/2024 | W.B.S.E.D.C.LTD | 5.89 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Itahar | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14642 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 27.05.2024 to 31.05.2024. |  |  | BILL/00133/2024-2025 | BP-2024-25-96 | 28/06/2024 | 28/06/2024 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Itahar | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14642 | New | Implementation of BASRATPUR and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000574/2022-2023 | 566/RD/PHE | 23/02/2023 | 21/08/2026 | M/S LOKENATH CONSTRUCTION | 352.8 | 107.28 | 30.41 | 20
8 | UTTAR DINAJPUR | Itahar | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14642 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BASRATPUR PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000535/2023-2024 | 617/RD/PHE | 05/03/2024 | 30/05/2025 | M/S UNIQUE 13 | 11.28 | 0 | 0 | 40
9 | UTTAR DINAJPUR | Itahar | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14642 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BASRATPUR PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000536/2023-2024 | 618/RD/PHE | 05/03/2024 | 15/04/2025 | M/S PINKI CONSTRUCTION | 11.28 | 0 | 0 | 40
10 | UTTAR DINAJPUR | Itahar | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14642 | New | Construction of Approach Road, Laying of Pipe Line, FHTC And Other allied Works of Basratpur PWSS Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000388/2024-2025 | 3558/RD/PHE | 05/12/2024 | 06/03/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 78.8 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Itahar | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14642 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Basratpur Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000313/2025-2026 | 2477/RD/PHE | 12/09/2025 | 11/03/2026 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 18.73 | 0 | 0 | 0
Total | [13 empty] | 591.02 | 130.74 | 22.12