## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Dhoarai Zone-II Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/14827 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 0.73 | 1.16 | 100
2 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Dhoarai Zone-II Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/14827 | New | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 1314/RD/PHE | 12/05/2023 | 12/05/2023 | Resource Division | 4.13 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Dhoarai Zone-II Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/14827 | New | Implementation of Dhoarai Zone-II and it's adjoining mouzas Pipe Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House at Head Work Site.) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000288/2022-2023 | 535/RD/PHE | 22/02/2023 | 23/05/2023 | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. DEBASISHGHOSHDG76@GMAIL.COM | 41.35 | 34.2 | 82.7 | 75
4 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Dhoarai Zone-II Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/14827 | New | Construction of Boundary Wall With Gate at Head Work Tube-Well Site under DHORAI ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000522/2023-2024 | 671/RD/PHE | 05/03/2024 | 19/04/2024 | SCON | 5.57 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Dhoarai Zone-II Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/14827 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I of Dhoarai (Zone-II) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017861) | Assistant Engineer - I | Junior Engineer-07 | ORD/000660/2023-2024 | 2743/MLMD | 14/08/2023 | 10/02/2024 | BINA CONSTRUCTION | 7.19 | 7.16 | 99.64 | 100
6 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Dhoarai Zone-II Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/14827 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Dhoarai, (Zone-II), Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02581/2023-2024 | BP-2023-24-473 | 26/01/2024 | 26/01/2024 | W.B.S.E.D.C.LTD | 0.14 | 0 | 0 | 0
Total | [13 empty] | 121.41 | 42.09 | 34.67