## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME | SM/15124 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000137/2022-2023 | 721/RD/PHE | 15/03/2023 | 15/03/2023 | Resource Division | 53.77 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME | SM/15124 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Bhatol, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/00737/2024-2025 | BP-2024-25-213 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 3.07 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME | SM/15124 | Augmentation | Additional Quotation for TW No-III of Bhatol water supply scheme in the district of Uttar Dinajpur. |  |  | BILL/02265/2024-2025 | BP-2024-25-545 | 01/10/2024 | 01/10/2024 | W.B.S.E.D.C.LTD | 3.83 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME | SM/15124 | Augmentation | Augmentation of Bhatol and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000304/2022-2023 | 553/RD/PHE | 23/02/2023 | 30/03/2026 | KAMIRUL SK & CO. | 502.82 | 0 | 0 | 5
5 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME | SM/15124 | Augmentation | Supply, installation & commissioning of electro-mechanical components of T/W no. I & II and Supply, installation, commissioning, Trial operation T/W no-III and making compound lighting arrangement at Headwork site of Augmentation of Bhatol Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011426) | Assistant Engineer - I | Junior Engineer-07 | ORD/001807/2023-2024 | 3694/MLMD | 29/11/2023 | 14/09/2025 | DEY ENTERPRISE.. | 34.56 | 0 | 0 | 62
6 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME | SM/15124 | Augmentation | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bhatol PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000248/2025-2026 | 2035/RD/PHE | 09/07/2025 | 05/01/2026 | KAMIRUL SK & CO. | 46.67 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME | SM/15124 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bhatol Water Supply Scheme(Augmentation) at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000281/2025-2026 | 1800/RD/PHE | 24/06/2025 | 21/12/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 18.73 | 0 | 0 | 0
Total | [13 empty] | 663.45 | 0 | 0