## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME | SM/15125 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000136/2022-2023 | 722/RD/PHE | 15/03/2023 | 15/03/2023 | Resource Division | 26.68 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME | SM/15125 | Augmentation | Supply, installation & commissioning of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Augmentation of Khanta Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011435) | Assistant Engineer - I | Junior Engineer-02 | ORD/000559/2023-2024 | 2509/MLMD | 04/08/2023 | 02/12/2023 | SHREE BISHNU CONSTRUCTION | 24.68 | 0 | 0 | 82
3 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME | SM/15125 | Augmentation | Construction of concrete pathway ,Land development and other ancillary works for Augmentation Of KHANTA RASAKHOWA Piped Water Supply Scheme at Head Work Site Pump House & 2nd Pump House Site under Islampur Sub-Division PHED.under Raiganj Division,PHE Dte U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000457/2024-2025 | 3775/RD/PHE | 19/12/2024 | 02/02/2025 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 26.93 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME | SM/15125 | Augmentation | Construction of Pump House (size 5.40m x 4.10m outer to outer) with sanitary and water supply arrangement according to departmental drawing with toilet at Head Work Site of Augmentation Of KHANTA-RASAKHOWA Piped Water Supply Schemes under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000288/2023-2024 | 2361/RD/PHE | 11/08/2023 | 10/10/2023 | BISWA PROKASH JHA | 5.75 | 0 | 0 | 100
5 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME | SM/15125 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Khanta PWSS , Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02466/2023-2024 | BP-2023-24-397 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 7.39 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Malda Mechanical | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME | SM/15125 | Augmentation | Additional Quotation for new service connection at KHANTA PH-III (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15125) |  |  | BILL/02079/2024-2025 | BP-2024-25-483 | 09/09/2024 | 09/09/2024 | W.B.S.E.D.C.LTD | 6.87 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME | SM/15125 | Augmentation | Augmentation of KHANTA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000306/2022-2023 | 570/RD/PHE | 23/02/2023 | 01/04/2025 | PRASANTA DUTTA | 363.57 | 0 | 0 | 65
8 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME | SM/15125 | Augmentation | Construction of Boundary Wall with Gate at Head Work Site & repair, renovation of boundary wall of 2nd Tube-Well Site under Augmentation of Khanta (Rasakhowa) PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000052/2025-2026 | 1542/RD/PHE | 11/06/2025 | 09/09/2025 | CHAPDUAR LABOUR CO- OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 12.61 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME | SM/15125 | Augmentation | Construction of Boundary Wall with Gate at Head Work Site & repair, renovation of boundary wall of 2nd Tube-Well Site under Augmentation of Khanta (Rasakhowa) PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000088/2025-2026 | 1437/RD/PHE | 30/05/2025 | 28/08/2025 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 12.61 | 0 | 0 | 0
10 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME | SM/15125 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Khanta-Rasakhowa Water Supply Scheme(Augmentation) at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Capacity-70 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000351/2025-2026 | 2497/RD/PHE | 12/09/2025 | 11/03/2026 | AJIT PRAMANIK | 30.93 | 0 | 0 | 0
11 | UTTAR DINAJPUR |  | Raiganj Division | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME | SM/15125 | Augmentation | Repairing for 2nd Pump House & Construction of Toilet at Kahanta (Rasakhowa) in connection with Augmentation of Khanta PWSS under Islampur Sub-Division under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000107/2023-2024 | 2051/RD/PHE | 19/07/2023 | 26/11/2024 | M/S DAS ENTERPRISE SUMAN974967@GMAIL.COM | 3.12 | 0 | 0 | 100
Total | [13 empty] | 521.14 | 0 | 0