## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | SARJAPUR Piped Water Supply Scheme | SM/15127 | New | Material Requisition To Resource Division |  |  | RTOR000157/2022-2023 | 886/RD/PHE | 27/03/2023 | 27/03/2023 | Resource Division | 47.4 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | SARJAPUR Piped Water Supply Scheme | SM/15127 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Sarjapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015948) | Assistant Engineer - I | Junior Engineer-02 | ORD/000545/2023-2024 | 2535/MLMD | 04/08/2023 | 29/10/2025 | MANIK CHANDRA SAHA. | 28.33 | 0 | 0 | 74
3 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | SARJAPUR Piped Water Supply Scheme | SM/15127 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 29/11/2025 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
Total | [13 empty] | 13006.8 | 0 | 0