## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | GODASAMAL Piped Water Supply Scheme | SM/15128 | New | Material Requisition To Resource Division |  |  | RTOR000156/2022-2023 | 889/RD/PHE | 27/03/2023 | 27/03/2023 | Resource Division | 50.62 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | GODASAMAL Piped Water Supply Scheme | SM/15128 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Godasamal Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016367) | Assistant Engineer - I | Junior Engineer-02 | ORD/000547/2023-2024 | 2503/MLMD | 04/08/2023 | 29/09/2025 | GHOSH BROTHERS... | 39.8 | 30.75 | 77.24 | 77
3 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | GODASAMAL Piped Water Supply Scheme | SM/15128 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 29/11/2025 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 304.12 | 2.35 | 35
4 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | GODASAMAL Piped Water Supply Scheme | SM/15128 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte | Assistant Engineer - I | Junior Engineer-04 | ORD/000397/2024-2025 | 3015/MLMD | 18/09/2024 | 18/11/2024 | RAMCHANDRA BASAK | 0.78 | 0.77 | 99.14 | 100
Total | [13 empty] | 13022.27 | 335.63 | 2.58