## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | BASATPUT Piped Water Supply Scheme | SM/15129 | New | Material Requisition To Resource Division |  |  | RTOR000178/2022-2023 | 978/RD/PHE | 30/03/2023 | 30/03/2023 | Resource Division | 48.44 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | BASATPUT Piped Water Supply Scheme | SM/15129 | New | Quotation for new service connection at BASATPUR PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15129) |  |  | BILL/02476/2024-2025 | BP-2024-25-568 | 14/11/2024 | 14/11/2024 | W.B.S.E.D.C.LTD | 14.54 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | BASATPUT Piped Water Supply Scheme | SM/15129 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 29/11/2025 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
4 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | BASATPUT Piped Water Supply Scheme | SM/15129 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Basatpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016384) | Assistant Engineer - I | Junior Engineer-02 | ORD/002475/2023-2024 | 99/MLMD | 11/01/2024 | 28/12/2025 | DIPALI CONSTRUCTION. | 29.09 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | BASATPUT Piped Water Supply Scheme | SM/15129 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 26/06/2024 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
6 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | BASATPUT Piped Water Supply Scheme | SM/15129 | New | Additional pipeline and other ancillary works at Basatpur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000406/2025-2026 | 2363/RD/PHE | 25/08/2025 | 09/10/2025 | MILAN GHOSH | 67.94 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | BASATPUT Piped Water Supply Scheme | SM/15129 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Basatpur Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 90 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000287/2025-2026 | 1809/RD/PHE | 24/06/2025 | 21/12/2025 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 33.59 | 0 | 0 | 0
Total | [13 empty] | 13129.47 | 0 | 0