## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of CHAPDUAR, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000472/2023-2024 | 4003196234 | 28/07/2023 | 26/10/2023 | W.B.S.E.D.C.LTD | 11.07 | 0 | 0 | 100
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of CHAPDUAR, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000474/2023-2024 | 4003196218 | 29/07/2023 | 27/10/2023 | W.B.S.E.D.C.LTD | 3.7 | 0 | 0 | 100
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 2235/RD/PHE | 02/08/2023 | 02/08/2023 | Resource Division | 32.15 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | shifting/Reorientation of 1 no 25 KVA DTR on Safety ground at Tubewell site-I of Chapduar water supply scheme under Birnagar CCC in the District of Uttar Dinajpur |  |  | BILL/02412/2024-2025 | BP-2024-25-566 | 29/10/2024 | 29/10/2024 | W.B.S.E.D.C.LTD | 1.06 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Chapduar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018241) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000653/2023-2024 | 2740/MLMD | 14/08/2023 | 27/04/2026 | HANNAN BUILDERS PVT. LTD. | 25.98 | 0 | 0 | 89
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000410/2024-2025 | 1746/RD/PHE | 14/06/2024 | 29/12/2024 | DEBASISH GHOSH | 2.6 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chapduar PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000429/2024-2025 | 3741/RD/PHE | 18/12/2024 | 02/05/2025 | UTTAM SAHA | 21.16 | 0 | 0 | 0
Total | [13 empty] | 97.73 | 0 | 0