## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | Implementation of CHAPDUAR and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000319/2022-2023 | 576/RD/PHE | 23/02/2023 | 01/07/2026 | UTTAM SAHA | 362.51 | 118.82 | 32.78 | 40
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Chapduar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018241) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000653/2023-2024 | 2740/MLMD | 14/08/2023 | 24/10/2026 | HANNAN BUILDERS PVT. LTD. | 25.98 | 19.73 | 75.95 | 89
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of CHAPDUAR, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000474/2023-2024 | 4003196218 | 29/07/2023 | 27/10/2023 | W.B.S.E.D.C.LTD | 3.7 | 3.7 | 100 | 100
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of CHAPDUAR, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000472/2023-2024 | 4003196234 | 28/07/2023 | 26/10/2023 | W.B.S.E.D.C.LTD | 11.07 | 11.07 | 100 | 100
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 2235/RD/PHE | 02/08/2023 | 02/08/2023 | Resource Division | 32.15 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000410/2024-2025 | 1746/RD/PHE | 14/06/2024 | 29/12/2024 | DEBASISH GHOSH | 2.6 | 0.39 | 15.17 | 0
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chapduar PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000429/2024-2025 | 3741/RD/PHE | 18/12/2024 | 02/05/2025 | UTTAM SAHA | 21.16 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAPDUAR PWSS at Raiganj Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000519/2023-2024 | 652/RD/PHE | 05/03/2024 | 21/05/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 22.58 | 5.96 | 26.39 | 100
9 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | shifting/Reorientation of 1 no 25 KVA DTR on Safety ground at Tubewell site-I of Chapduar water supply scheme under Birnagar CCC in the District of Uttar Dinajpur |  |  | BILL/02412/2024-2025 | BP-2024-25-566 | 29/10/2024 | 29/10/2024 | W.B.S.E.D.C.LTD | 1.06 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Raiganj | Raiganj Division | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Sheme in different Block in the District of Uttar Dinajpur under Raiganj Division,PHE Dte.. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000518/2024-2025 | 58/RD/PHE | 03/01/2025 | 12/02/2026 | TECHVISION | 5 | 0 | 0 | 83
Total | [13 empty] | 487.8 | 159.67 | 32.73