## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/15147 | New | Implementation of BHULKI and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd Tube Well) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000395/2022-2023 | 747/RD/PHE | 16/03/2023 | 10/03/2026 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 463.74 | 168.81 | 36.4 | 20
2 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/15147 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Bhulki Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018418) | Assistant Engineer - I | Junior Engineer-02 | ORD/000189/2023-2024 | 2112/MLMD | 05/07/2023 | 01/01/2024 | SHREE BISHNU CONSTRUCTION | 26.9 | 24.25 | 90.16 | 90
3 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/15147 | New | Construction of Reinforcement Concrete Pathway at Headwork Site for Bhulki PWSS of Islampur Sub-Division under Raiganj Division, PHE Dte.(NEW Scheme) | Assistant Engineer ISD |  | ORD/000393/2023-2024 | 2654/RD/PHE | 15/09/2023 | 15/10/2023 | R. R. CONSTRUCTION | 9.98 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/15147 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of BHULKI, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001555/2023-2024 | 4003209110 | 21/09/2023 | 20/12/2023 | W.B.S.E.D.C.LTD | 3.54 | 3.54 | 100 | 100
5 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/15147 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BHULKI, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001556/2023-2024 | 4003194764 | 19/09/2023 | 18/12/2023 | W.B.S.E.D.C.LTD | 5.92 | 5.92 | 100 | 100
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/15147 | New | Material Requisition To Resource Division |  |  | RTOR000129/2022-2023 | 634/RD/PHE | 02/03/2023 | 02/03/2023 | Resource Division | 58.74 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/15147 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BHULKI PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000516/2023-2024 | 647/RD/PHE | 05/03/2024 | 14/03/2025 | SANDIP SARKAR | 22.58 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/15147 | New | Laying of Additional pipeline with other ancillary works at different mouzas of BHULKI PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000375/2024-2025 | 3494/RD/PHE | 02/12/2024 | 16/01/2025 | S.B.CONSTRUCTION | 34.78 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/15147 | New | Laying additional pipe line with FHTC for New Scheme Of Bhulki Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000467/2024-2025 | 3785/RD/PHE | 19/12/2024 | 02/02/2025 | S M CONSTRUCTION RAJ.GSHOSH325@GMAIL.COM | 34.76 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/15147 | New | Construction of concrete pathway at 2nd TW Site Pump House for BHULKI Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000366/2024-2025 | 3485/RD/PHE | 02/12/2024 | 17/12/2024 | BHAGYA LAXMI ENTERPRISE | 4.28 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/15147 | New | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS |  |  | BILL/01222/2023-2024 | BP-2024-25-24 | 24/04/2024 | 24/04/2024 | EXECUTIVE ENGINEER PWD ROADS | 9.3 | 0 | 0 | 0
12 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/15147 | New | Road Restoration with Earth Filling at Head Work Site, & 2nd Tube-Well Site under New Scheme of Bhulki PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000246/2025-2026 | 1466/RD/PHE | 04/06/2025 | 24/06/2025 | DUTTA ENTERPRISE | 2.5 | 0 | 0 | 0
Total | [13 empty] | 677.03 | 202.52 | 29.91