## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer RSD |  | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 04/10/2022 | RADIANT | 47.87 | 4.48 | 9.36 | 100
2 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Pajol, Itahar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | ORD/001740/2023-2024 | 4003233393 | 22/09/2023 | 21/12/2023 | W.B.S.E.D.C.LTD | 6.22 | 6.22 | 100 | 100
3 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Pajol, Itahar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | ORD/001742/2023-2024 | 4003233390 | 22/09/2023 | 21/12/2023 | W.B.S.E.D.C.LTD | 7.92 | 7.92 | 100 | 100
4 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 | New | Material Requisition To Resource Division |  |  | RTOR000139/2022-2023 | 786/RD/PHE | 18/03/2023 | 18/03/2023 | Resource Division | 137.43 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 | New | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under PAJOL PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000544/2023-2024 | 630/RD/PHE | 05/03/2024 | 01/07/2024 | R. R. CONSTRUCTION | 12.24 | 6.96 | 56.86 | 70
6 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 | New | DI Pipe Carrying RCC Structure Over Sooin River of Pajol PWSS at Itahar Block under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. |  | Junior Engineer, RSD | ORD/000121/2024-2025 | 3011/RD/PHE | 03/10/2024 | 02/11/2024 | BHOLA PAUL | 6.06 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 24.06.2024 to 28.06.2024. |  |  | BILL/00227/2024-2025 | BP-2024-25-154 | 30/07/2024 | 30/07/2024 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 18.06.2024 to 21.06.2024. |  |  | BILL/00226/2024-2025 | BP-2024-25-153 | 30/07/2024 | 30/07/2024 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 22.07.2024 to 26.07.2024. |  |  | BILL/00273/2024-2025 | BP-2024-25-179 | 30/08/2024 | 30/08/2024 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 | New | Implementation of PAJOL and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000320/2022-2023 | 556/RD/PHE | 23/02/2023 | 01/07/2026 | BHOLA PAUL | 315.3 | 114.82 | 36.42 | 44
11 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer HQ | Estimator | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 28/06/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
12 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound yard lighting arrangement at T/W no. I of Pajol Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018893) | Assistant Engineer - I | Junior Engineer-02 | ORD/000742/2023-2024 | 2803/MLMD | 17/08/2023 | 28/11/2025 | NIRMAN. | 25.82 | 18.24 | 70.63 | 77
13 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Pajol PWSS at Itahar Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000422/2024-2025 | 3734/RD/PHE | 18/12/2024 | 02/05/2025 | BHOLA PAUL | 48.58 | 0 | 0 | 0
14 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Pajol Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj, Capacity- 50 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000266/2025-2026 | 1632/RD/PHE | 20/06/2025 | 17/12/2025 | AJIT PRAMANIK | 20.74 | 0 | 0 | 0
15 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 | New | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under PAJOL PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000545/2023-2024 | 631/RD/PHE | 05/03/2024 | 03/06/2024 | M/S NATARAJ CONSTRUCTION DEBUABCD.1234@REDIFFMAIL.COM | 12.24 | 0 | 0 | 90
Total | [13 empty] | 645.52 | 158.64 | 24.58