## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15211 | New | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 1320/RD/PHE | 12/05/2023 | 12/05/2023 | Resource Division | 35.97 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15211 | New | Construction of concrete pathway with earth Filling at Head Work Site Pump House & 2nd TW Site Pump House for Shiripur Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division, PHE Dte., U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000359/2024-2025 | 3310/RD/PHE | 20/11/2024 | 20/12/2024 | NIRMAN ENTERPRISE | 10.84 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Karandighi | Raiganj Division | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15211 | New | Additional pipeline and other ancillary works at Shiripur piped water Supply Scheme Under Islampur Sub-Division under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000356/2024-2025 | 3309/RD/PHE | 20/11/2024 | 20/12/2024 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 12.42 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15211 | New | Quotation for new service connection at SHRIPUR PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15211) |  |  | BILL/02083/2024-2025 | BP-2024-25-482 | 09/09/2024 | 09/09/2024 | W.B.S.E.D.C.LTD | 3.73 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15211 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Shripur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018397) | Assistant Engineer - I | Junior Engineer-02 | ORD/000693/2023-2024 | 2768/MLMD | 14/08/2023 | 28/11/2025 | M/S TRILOCHAN CONSTRUCTION CO. | 27.01 | 0 | 0 | 77
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15211 | New | Implementation of SHRIPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Tube-Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work & 2nd TubeWell) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000384/2023-2024 | 2629/RD/PHE | 13/09/2023 | 13/09/2024 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 403.31 | 0 | 0 | 45
7 | UTTAR DINAJPUR | Karandighi | Raiganj Division | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15211 | New | Construction of Boundary Wall with Gate at Head Work Site& 2nd Tube-Well Site under Shripur PWSS at Karandighi Block under Raiganj Division, P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000051/2025-2026 | 1541/RD/PHE | 11/06/2025 | 09/09/2025 | BISWA PROKASH JHA | 24.48 | 0 | 0 | 0
Total | [13 empty] | 517.75 | 0 | 0