## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Laying Rising Main of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000514/2022-2023 | 857/RD/PHE | 24/03/2023 | 23/05/2023 | M/S DAS CONSTRUCTION ITAHAR | 4.52 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of DHOABISHUA, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000476/2023-2024 | 4003196207 | 28/07/2023 | 26/10/2023 | W.B.S.E.D.C.LTD | 8.77 | 0 | 0 | 100
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of DHOABISHUA, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000477/2023-2024 | 4003196209 | 28/07/2023 | 26/10/2023 | W.B.S.E.D.C.LTD | 6.06 | 0 | 0 | 100
4 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 1680/RD/PHE | 19/06/2023 | 19/06/2023 | Resource Division | 42.41 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Kokra, 2.Bishahar, 3. Dhoabishua in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000290/2022-2023 | 539/RD/PHE | 22/02/2023 | 13/11/2024 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 0 | 65
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Laying Pipeline at village-Aulabari of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000408/2022-2023 | 763/RD/PHE | 17/03/2023 | 16/05/2023 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 50.29 | 0 | 0 | 65
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Construction of OHR (Capacity-250Cum) with pipeline of Dhoabishua Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000509/2022-2023 | 852/RD/PHE | 24/03/2023 | 18/03/2025 | M/S RATAN SARKAR & SON | 95.77 | 0 | 0 | 45
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Laying pipe line of village-Balihar & Shialtore of DHOABISHUA PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000519/2022-2023 | 873/RD/PHE | 27/03/2023 | 01/03/2025 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 46.8 | 0 | 0 | 65
9 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Laying distribution of pipe line of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000470/2022-2023 | 819/RD/PHE | 22/03/2023 | 25/01/2025 | M/S HINDUSTHAN CONSTRUCTION HCONSTRUCTION.RNJ@GMAIL.COM | 57.91 | 0 | 0 | 60
10 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Laying pipe line of village- Deogaon & Ekar of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000536/2022-2023 | 948/RD/PHED | 29/03/2023 | 23/03/2024 | S. B. CONSTRUCTION | 50.92 | 0 | 0 | 55
11 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Dhoabishua Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018369) | Assistant Engineer - I | Junior Engineer-07 | ORD/000662/2023-2024 | 2744/MLMD | 14/08/2023 | 10/02/2024 | TAPAN BISWAS. | 24.25 | 0 | 0 | 75
12 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Construction of boundary wall and pump house at head work site of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000486/2022-2023 | 825/RD/PHE | 22/03/2023 | 20/04/2024 | M/S. ROY & CO. | 24.75 | 0 | 0 | 95
13 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Construction of boundary wall and pump house at 2nd tube-well site of DHOABISHUA PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000413/2022-2023 | 768/RD/PHE | 17/03/2023 | 16/05/2023 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 11 | 0 | 0 | 80
14 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Providing Functional House hold tap connection at village- Aulabari of DHOABISHUA Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000418/2022-2023 | 773/RD/PHE | 17/03/2023 | 30/04/2025 | BITTU ENTERPRISE BISWAJIT.RNJ@GMAIL.COM | 15.25 | 0 | 0 | 0
15 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Providing functional house hold tap connection at Village-Balihar & Shialtore of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000528/2022-2023 | 878/RD/PHE | 27/03/2023 | 29/04/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 15.99 | 0 | 0 | 0
16 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Providing functional house hold tap connection of village-Dhoabishua of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000546/2022-2023 | 958/RD/PHE | 29/03/2023 | 30/04/2025 | M/S P.S. ENTERPRISE | 15.41 | 0 | 0 | 0
17 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Providing Functional house Hold Tap Connections at village- Balihar and Ekar of DHOABISHUA Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000541/2022-2023 | 953/RD/PHE | 29/03/2023 | 29/06/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 16.18 | 0 | 0 | 0
18 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte | Assistant Engineer - I | Junior Engineer-02 | ORD/000648/2024-2025 | 3309/MLMD | 30/09/2024 | 31/10/2024 | DAS CONSTRUCTION | 0.39 | 0 | 0 | 0
19 | UTTAR DINAJPUR | Raiganj | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15212 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Dhoabishua PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000436/2024-2025 | 3743/RD/PHE | 18/12/2024 | 02/05/2025 | DONE ENTERPRISE | 14.77 | 0 | 0 | 0
Total | [13 empty] | 581.04 | 0 | 0