## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15213 | New | Material Requisition To Resource Division |  |  | RTOR000130/2022-2023 | 635/RD/PHE | 02/03/2023 | 02/03/2023 | Resource Division | 49.14 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15213 | New | Implementation of DHAUTA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd Tube Well) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000360/2023-2024 | 2476/RD/PHE | 24/08/2023 | 24/11/2025 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 448.76 | 0 | 0 | 62
3 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15213 | New | Quotation for new service connection at DHAUTA PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15213). |  |  | BILL/01105/2024-2025 | BP-2024-25-268 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 7.37 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15213 | New | Quotation for new service connection at DHAUTA PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15213). |  |  | BILL/01104/2024-2025 | BP-2024-25-267 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 8.09 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15213 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II of Dhauta Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018375) | Assistant Engineer - I,Assistant Engineer - II | Junior Engineer-02,Junior Engineer-07 | ORD/000657/2023-2024 | 2742/MLMD | 14/08/2023 | 31/12/2025 | M/S TRILOCHAN CONSTRUCTION CO. | 24.36 | 0 | 0 | 90
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15213 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DHAUTA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000514/2023-2024 | 643/RD/PHE | 05/03/2024 | 19/07/2025 | UP-SHINE ENGINEERS CO-OP.&CONTRUCTION SOCIETY LTD. | 22.58 | 0 | 0 | 80
7 | UTTAR DINAJPUR | Karandighi | Raiganj Division | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15213 | New | Laying Upvc Pipe Line And Others Anciliary Warks Of Dhauta Pwss Within Karandighi Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000496/2024-2025 | 29/RD/PHE | 02/01/2025 | 16/02/2025 | AJIT PRAMANIK | 94.84 | 0 | 0 | 0
Total | [13 empty] | 655.12 | 0 | 0