## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MAHARAJPUR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15214 | New | Implementation of MAHARAJPUR and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000323/2022-2023 | 560/RD/PHE | 23/02/2023 | 30/06/2026 | UTTAM SAHA | 600.95 | 0 | 0 | 40
2 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MAHARAJPUR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15214 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Dakshin Goalpara, 2. Bhattagidighi, 3. Maharajpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000291/2022-2023 | 540/RD/PHE | 22/02/2023 | 13/11/2024 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 0 | 80
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | MAHARAJPUR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15214 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Maharajpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018311) | Assistant Engineer - I | Junior Engineer-07 | ORD/000686/2023-2024 | 2761/MLMD | 14/08/2023 | 10/02/2024 | M/S DYNAMIC ENGINEERS ENTERPRISE.... | 26.71 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MAHARAJPUR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15214 | New | Material Requisition To Resource Division |  |  | RTOR000151/2022-2023 | 864/RD/PHE | 25/03/2023 | 25/03/2023 | Resource Division | 46.67 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | MAHARAJPUR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15214 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Maharajpur PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000445/2024-2025 | 3757/RD/PHED | 18/12/2024 | 01/02/2025 | UTTAM SAHA | 22.87 | 0 | 0 | 0
Total | [13 empty] | 776.8 | 0 | 0