## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 1319/RD/PHE | 12/05/2023 | 12/05/2023 | Resource Division | 45.19 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Additional pipeline and other ancillary works at Rahutara piped water Supply Scheme Under Islampur SubDivision under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000353/2024-2025 | 3307/RD/PHE | 20/11/2024 | 04/01/2025 | AJIT PRAMANIK | 20.98 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under RAUTARA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD |  | ORD/000560/2023-2024 | 661/RD/PHE | 05/03/2024 | 19/04/2024 | M/S PRATIMA CHOUDHURY | 11.29 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Construction of concrete pathway at Head Work Site Pump House & 2nd TW Site Pump House for Rahutara Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHE Dte., U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000354/2024-2025 | 3308/RD/PHE | 20/11/2024 | 04/01/2025 | AJIT PRAMANIK | 16.57 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Quotation for new service connection at RAUTARA PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15306) |  |  | BILL/01109/2024-2025 | BP-2024-25-266 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 13.44 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Quotation for new service connection at RAUTARA PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15306) |  |  | BILL/01108/2024-2025 | BP-2024-25-265 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 7.63 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Implementation of RAUTARA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.( Tube-Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work & 2nd TubeWell) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000365/2023-2024 | 2481/RD/PHE | 24/08/2023 | 01/04/2026 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 451.99 | 186.75 | 41.32 | 60
8 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Rautara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018384) | Assistant Engineer - I | Junior Engineer-02 | ORD/000753/2023-2024 | 2819/MLMD | 17/08/2023 | 26/06/2026 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 25.43 | 0 | 0 | 42
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under RAUTARA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000561/2023-2024 | 662/RD/PHE | 05/03/2024 | 09/09/2025 | M/S SANTI TRADERS | 11.29 | 0 | 0 | 80
Total | [13 empty] | 603.8 | 186.75 | 30.93