## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 1319/RD/PHE | 12/05/2023 | 12/05/2023 | Resource Division | 45.19 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Additional pipeline and other ancillary works at Rahutara piped water Supply Scheme Under Islampur SubDivision under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000353/2024-2025 | 3307/RD/PHE | 20/11/2024 | 04/01/2025 | AJIT PRAMANIK | 20.98 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under RAUTARA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD |  | ORD/000560/2023-2024 | 661/RD/PHE | 05/03/2024 | 19/04/2024 | M/S PRATIMA CHOUDHURY | 11.29 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Construction of concrete pathway at Head Work Site Pump House & 2nd TW Site Pump House for Rahutara Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHE Dte., U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000354/2024-2025 | 3308/RD/PHE | 20/11/2024 | 04/01/2025 | AJIT PRAMANIK | 16.57 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Quotation for new service connection at RAUTARA PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15306) |  |  | BILL/01109/2024-2025 | BP-2024-25-266 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 13.44 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Quotation for new service connection at RAUTARA PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15306) |  |  | BILL/01108/2024-2025 | BP-2024-25-265 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 7.63 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Implementation of RAUTARA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.( Tube-Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work & 2nd TubeWell) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000365/2023-2024 | 2481/RD/PHE | 24/08/2023 | 01/04/2026 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 451.99 | 186.75 | 41.32 | 60
8 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Rautara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018384) | Assistant Engineer - I | Junior Engineer-02 | ORD/000753/2023-2024 | 2819/MLMD | 17/08/2023 | 26/06/2026 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 25.43 | 0 | 0 | 42
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under RAUTARA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000561/2023-2024 | 662/RD/PHE | 05/03/2024 | 09/09/2025 | M/S SANTI TRADERS | 11.29 | 0 | 0 | 80
10 | UTTAR DINAJPUR | Karandighi | Raiganj Division | RAUTARA Pipe Water Supply Scheme | SM/15306 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Sheme in different Block in the District of Uttar Dinajpur under Raiganj Division,PHE Dte.. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000518/2024-2025 | 58/RD/PHE | 03/01/2025 | 12/02/2026 | TECHVISION | 5 | 0 | 0 | 83
Total | [13 empty] | 608.8 | 186.75 | 30.67