## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | KADERGANJ Pipe Water Supply Scheme | SM/15307 | New | Material Requisition To Resource Division |  |  | RTOR000124/2022-2023 | 641/RD/PHE | 02/03/2023 | 02/03/2023 | Resource Division | 50.52 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | KADERGANJ Pipe Water Supply Scheme | SM/15307 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Kaderganj Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018390) | Assistant Engineer - I | Junior Engineer-02 | ORD/000673/2023-2024 | 2752/MLMD | 14/08/2023 | 26/06/2026 | M/S PARIMAL DAS. | 25.7 | 19.57 | 76.14 | 76
3 | UTTAR DINAJPUR | Karandighi | Raiganj Division | KADERGANJ Pipe Water Supply Scheme | SM/15307 | New | Construction of concrete pathway ,Land development and other ancillary works for KADERGANJ Piped Water Supply Scheme at Head Work Site Pump House & 2nd Pump House Site under Islampur Sub-Division PHE Dte. under Raiganj Division,PHE Dte.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000463/2024-2025 | 3781/RD/PHE | 19/12/2024 | 18/01/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 12.65 | 0 | 0 | 0
Total | [13 empty] | 88.88 | 19.57 | 22.02