## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | MAJRA Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. | SM/15516 | New | Material Requisition To Resource Division |  |  | RTOR000149/2022-2023 | 846/RD/PHE | 24/03/2023 | 24/03/2023 | Resource Division | 64.22 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | MAJRA Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. | SM/15516 | New | Quotation for new service connection at MAJRA PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00214/2024-2025 | BP-2024-25-123 | 24/04/2024 | 24/04/2024 | W.B.S.E.D.C.LTD | 17.66 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | MAJRA Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. | SM/15516 | New | Quotation for new service connection at MAJRA PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00026/2024-2025 | BP-2024-25-41 | 08/04/2024 | 08/04/2024 | W.B.S.E.D.C.LTD | 15.98 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | MAJRA Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. | SM/15516 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Majra Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015895) | Assistant Engineer - I | Junior Engineer-02 | ORD/000521/2023-2024 | 2517/MLMD | 04/08/2023 | 02/12/2023 | GHOSH BROTHERS... | 39.77 | 0 | 0 | 83
5 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | MAJRA Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. | SM/15516 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 29/11/2025 | M/S GHOSH AND CO. | 12931.07 | 352.23 | 2.72 | 35
6 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | MAJRA Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. | SM/15516 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 05/10/2024 | SISIR KUMAR DUTTA | 4.8 | 0.38 | 7.94 | 0
Total | [13 empty] | 13073.5 | 352.61 | 2.7