## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16199 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer RSD |  | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 04/10/2022 | RADIANT | 47.87 | 0.85 | 1.79 | 100
2 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16199 | New | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 1678/RD/PHE | 19/06/2023 | 19/06/2023 | Resource Division | 3.19 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16199 | New | Implementation of Pakhuria and it's adjoining mouzas Pipe Water Supply Scheme at Itahar Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House at Head Work Site.) | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD | ORD/000273/2022-2023 | 679/RD/PHE | 06/03/2023 | 04/06/2023 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 48.68 | 31.72 | 65.16 | 40
4 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16199 | New | Construction of Boundary Wall With Gate at Head Work Tube-Well Site under PAKHURIA PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000495/2023-2024 | 615/RD/PHE | 05/03/2024 | 19/04/2024 | GOPES SAHA | 5.57 | 5.56 | 99.79 | 100
5 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16199 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Pakhuria , Itahar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02464/2023-2024 | BP-2023-24-393 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 4.16 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Itahar | Raiganj Division | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16199 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Pakhuria Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj, Capacity- 5 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000265/2025-2026 | 1631/RD/PHE | 20/06/2025 | 17/12/2025 | AJIT PRAMANIK | 12.4 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16199 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. III of Source augmentation of Pakhuria Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016131) | Assistant Engineer - I | Junior Engineer-02 | ORD/000439/2023-2024 | 2450/MLMD | 04/08/2023 | 31/05/2024 | M/S SABANA CONSTRUCTION | 6.89 | 6.5 | 94.28 | 100
Total | [13 empty] | 128.76 | 44.63 | 34.66