## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16219 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 0 | 0 | 100
2 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16219 | New | Material Requisition To Resource Division |  |  | RTOR000141/2022-2023 | 808/RD/PHE | 21/03/2023 | 21/03/2023 | Resource Division | 46.32 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16219 | New | Implementation of HARINARAYANPUR(Zone- I) and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000013/2023-2024 | 1275/RD/PHE | 08/05/2023 | 01/01/2026 | UJJWAL DAS | 344.33 | 0 | 0 | 50
4 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16219 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Harinarayanpur Zone-I Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018695) | Assistant Engineer - I | Junior Engineer-07 | ORD/000671/2023-2024 | 2750/MLMD | 14/08/2023 | 10/02/2024 | DAS CONSTRUCTION | 24.35 | 0 | 0 | 89
5 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16219 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Harinarayanpur (Zone-I), Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03659/2023-2024 | BP-2023-24-635 | 06/03/2024 | 06/03/2024 | W.B.S.E.D.C.LTD | 0.45 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16219 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Harinarayanpur (Zone-I), Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03658/2023-2024 | BP-2023-24-634 | 06/03/2024 | 06/03/2024 | W.B.S.E.D.C.LTD | 0.56 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16219 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under HARINARAYANPUR ZONE-I PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000051/2024-2025 | 1710/RD/PHE | 10/06/2024 | 25/07/2024 | ADYA MAA CONSTRUCTION | 24.47 | 0 | 0 | 100
8 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16219 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Harinarayanpur Zone-1 PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000489/2024-2025 | 22/RD/PHE | 02/01/2025 | 16/02/2025 | UJJWAL DAS | 47.1 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16219 | New | Trial Run For Harinarayanpur Zone-I PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 month | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000688/2024-2025 | 534/RD/PHE | 12/02/2025 | 13/05/2025 | UJJWAL DAS | 0.88 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16219 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Harinarayanpur Zone-I Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Block:- Raiganj,Capacity- 45 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000263/2025-2026 | 1628/RD/PHE | 19/06/2025 | 16/12/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 19.35 | 0 | 0 | 0
Total | [13 empty] | 570.84 | 0 | 0