## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 3.47 | 5.51 | 100
2 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | Material Requisition To Resource Division |  |  | RTOR000142/2022-2023 | 809/RD/PHE | 21/03/2023 | 21/03/2023 | Resource Division | 20.28 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | Implementation of HARINARAYANPUR(Zone- II) and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000014/2023-2024 | 1276/RD/PHE | 08/05/2023 | 24/10/2025 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 306.66 | 185.71 | 60.56 | 10
4 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under HARINARAYANPUR ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000509/2023-2024 | 634/RD/PHE | 05/03/2024 | 19/04/2024 | M/S R.D. CONSTRUCTION | 24.48 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Harinarayanpur, (Zone-II), Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02579/2023-2024 | BP-2023-24-471 | 26/01/2024 | 26/01/2024 | W.B.S.E.D.C.LTD | 11.36 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Harinarayanpur, (Zone-II), Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02578/2023-2024 | BP-2023-24-470 | 26/01/2024 | 26/01/2024 | W.B.S.E.D.C.LTD | 12.34 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Harinarayanpur Zone- II Water Supply Scheme in the District of Malda under Uttar Dinajpur Mechanical Division, PHE Dte. (TSM/018697) | Assistant Engineer - I | Junior Engineer-07 | ORD/000670/2023-2024 | 2749/MLMD | 14/08/2023 | 28/11/2025 | JOYSHREE CONCERN. | 22.21 | 18.08 | 81.41 | 89
8 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Harinarayanpur Zone-2 PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000491/2024-2025 | 24/RD/PHE | 02/01/2025 | 16/02/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 22.97 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | Trial Run For Harinarayanpur Zone-II PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 month | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000687/2024-2025 | 533/RD/PHE | 12/02/2025 | 13/05/2025 | M/S P.S. ENTERPRISE | 0.88 | 0 | 0 | 0
Total | [13 empty] | 484.21 | 207.26 | 42.8