## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 3.47 | 5.51 | 100
2 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | Implementation of HARINARAYANPUR(Zone- II) and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000014/2023-2024 | 1276/RD/PHE | 08/05/2023 | 21/07/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 306.66 | 185.71 | 60.56 | 10
3 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Harinarayanpur Zone- II Water Supply Scheme in the District of Malda under Uttar Dinajpur Mechanical Division, PHE Dte. (TSM/018697) | Assistant Engineer - I | Junior Engineer-07 | ORD/000670/2023-2024 | 2749/MLMD | 14/08/2023 | 28/11/2025 | JOYSHREE CONCERN. | 22.21 | 18.08 | 81.41 | 89
4 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | Material Requisition To Resource Division |  |  | RTOR000142/2022-2023 | 809/RD/PHE | 21/03/2023 | 21/03/2023 | Resource Division | 20.28 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under HARINARAYANPUR ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000509/2023-2024 | 634/RD/PHE | 05/03/2024 | 19/04/2024 | M/S R.D. CONSTRUCTION | 24.48 | 0 | 0 | 100
6 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Harinarayanpur, (Zone-II), Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02578/2023-2024 | BP-2023-24-470 | 26/01/2024 | 26/01/2024 | W.B.S.E.D.C.LTD | 12.34 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Harinarayanpur, (Zone-II), Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02579/2023-2024 | BP-2023-24-471 | 26/01/2024 | 26/01/2024 | W.B.S.E.D.C.LTD | 11.36 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Harinarayanpur Zone-2 PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000491/2024-2025 | 24/RD/PHE | 02/01/2025 | 16/02/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 22.97 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Sheme in different Block in the District of Uttar Dinajpur under Raiganj Division,PHE Dte.. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000518/2024-2025 | 58/RD/PHE | 03/01/2025 | 12/02/2026 | TECHVISION | 5 | 0 | 0 | 83
10 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 | New | Trial Run For Harinarayanpur Zone-II PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 month | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000687/2024-2025 | 533/RD/PHE | 12/02/2025 | 13/05/2025 | M/S P.S. ENTERPRISE | 0.88 | 0 | 0 | 0
Total | [13 empty] | 489.2 | 207.26 | 42.37