## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16221 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer RSD |  | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 04/10/2022 | RADIANT | 47.87 | 4.34 | 9.07 | 100
2 | UTTAR DINAJPUR | Itahar | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16221 | New | Implementation of SONAPUR and its adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000011/2023-2024 | 1273/RD/PHE | 08/05/2023 | 02/01/2026 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 362.18 | 202.77 | 55.99 | 50
3 | UTTAR DINAJPUR | Itahar | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16221 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer HQ | Estimator | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 28/06/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0.79 | 16.51 | 100
4 | UTTAR DINAJPUR | Itahar | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16221 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12 months (Period from 17.10.2023 to 16.10.2024) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000627/2023-2024 | 2876/RD/PHE | 17/10/2023 | 17/10/2024 | ARNAB DUTTA | 4.8 | 0 | 0 | 100
5 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16221 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Sonapur, Itahar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | ORD/001743/2023-2024 | 4003233395 | 22/09/2023 | 21/12/2023 | W.B.S.E.D.C.LTD | 9.43 | 9.43 | 100 | 100
6 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16221 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Sonapur, Itahar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | ORD/001744/2023-2024 | 4003233398 | 22/09/2023 | 21/12/2023 | W.B.S.E.D.C.LTD | 5.12 | 5.12 | 100 | 100
7 | UTTAR DINAJPUR | Itahar | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16221 | New | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 1569/RD/PHE | 31/05/2023 | 31/05/2023 | Resource Division | 22.31 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16221 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound yard lighting arrangement at T/W no. I of Sonapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/000318/2024-2025 | 2945/MLMD | 11/09/2024 | 28/12/2025 | MANIK CHANDRA SAHA. | 26.45 | 4.85 | 18.34 | 70
9 | UTTAR DINAJPUR | Itahar | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16221 | New | Construction Of Approach Road, Laying of Pipe Line,Fhtc and Other Allied Works Of Sonapur Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000394/2024-2025 | 3565/RD/PHE | 05/12/2024 | 19/01/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 76.02 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Itahar | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16221 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SONAPUR PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RWS | ORD/000506/2023-2024 | 629/RD/PHE | 05/03/2024 | 14/04/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 22.58 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Itahar | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16221 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 11/04/2024 | HORIZEN | 5 | 0.3 | 6.08 | 100
12 | UTTAR DINAJPUR | Itahar | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16221 | New | Demand for placing necessary fund for the work Permanent restoration of damaged hard shoulder/flank of L039-PURBADURLAVPUR TO UTTAR MAHESHPUR (Package No. WB15303 : Under DLP) caused due to pipe laying by PHED under Sonapur PWSS at different stretched of road under WBSRDA Uttar Dinajpur Division. |  |  | BILL/00472/2024-2025 | BP-2024-25-273 | 08/10/2024 | 08/10/2024 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 0.9 | 0 | 0 | 0
13 | UTTAR DINAJPUR | Itahar | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16221 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Sonapur Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Capacity- 40 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000307/2025-2026 | 2474/RD/PHE | 12/09/2025 | 11/03/2026 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 18.73 | 0 | 0 | 0
Total | [13 empty] | 606.18 | 227.61 | 37.55