## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16222 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 3.8 | 6.02 | 100
2 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16222 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Bahala (Zone-I) PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001957/2023-2024 | 4003279110 | 06/12/2023 | 05/03/2024 | W.B.S.E.D.C.LTD | 5.13 | 5.13 | 100 | 100
3 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16222 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Bahala (Zone-I) PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001958/2023-2024 | 4003279099 | 06/12/2023 | 05/03/2024 | W.B.S.E.D.C.LTD | 8.75 | 8.75 | 100 | 100
4 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16222 | New | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 2240/RD/PHE | 02/08/2023 | 02/08/2023 | Resource Division | 22.87 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16222 | New | Implementation of BAHALA ZONE-I and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000015/2023-2024 | 1277/RD/PHE | 08/05/2023 | 01/07/2026 | BHOLA PAUL | 310.32 | 154.09 | 49.65 | 30
6 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16222 | New | Additional quotation of Bahala Zone-I PWSS TW-I in the district of Uttar Dinajpur. |  |  | BILL/01789/2024-2025 | BP-2024-25-438 | 20/08/2024 | 20/08/2024 | W.B.S.E.D.C.LTD | 5.27 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16222 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Bahala Zone- I Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018495) | Assistant Engineer - I | Junior Engineer-07 | ORD/000616/2023-2024 | 2728/MLMD | 14/08/2023 | 18/01/2026 | S PATHAK & CO. | 24.05 | 15.96 | 66.34 | 88
8 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16222 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 11/04/2024 | HORIZEN | 5 | 0.33 | 6.64 | 100
9 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16222 | New | Balance distribution System Of Laying pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAHALA ZONE-I PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000511/2023-2024 | 636/RD/PHE | 05/03/2024 | 19/04/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 22.72 | 0 | 0 | 100
Total | [13 empty] | 467.15 | 188.05 | 40.26