## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16223 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 4.1 | 6.51 | 100
2 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16223 | New | Implementation of BAHALA ZONE-II and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000016/2023-2024 | 1278/RD/PHE | 08/05/2023 | 01/07/2026 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 345.32 | 117.51 | 34.03 | 52
3 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16223 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Bahala Zone- II Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018496) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000614/2023-2024 | 2727/MLMD | 14/08/2023 | 18/01/2026 | S PATHAK & CO. | 24.05 | 17.98 | 74.73 | 88
4 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16223 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Bahala (Zone-II) PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001959/2023-2024 | 4003279119 | 06/12/2023 | 05/03/2024 | W.B.S.E.D.C.LTD | 3.29 | 3.29 | 100 | 100
5 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16223 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Bahala (Zone-II) PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001960/2023-2024 | 4003279126 | 06/12/2023 | 05/03/2024 | W.B.S.E.D.C.LTD | 4.28 | 4.28 | 100 | 100
6 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16223 | New | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 2241/RD/PHE | 02/08/2023 | 02/08/2023 | Resource Division | 23.33 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16223 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000410/2024-2025 | 1746/RD/PHE | 14/06/2024 | 29/12/2024 | DEBASISH GHOSH | 2.6 | 0.37 | 14.37 | 0
8 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16223 | New | Balance distribution System Of Laying pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAHALA ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000510/2023-2024 | 635/RD/PHE | 05/03/2024 | 16/10/2024 | M/S GHOSH CONSTRUCTION GHOSH1.RNJ@GMAIL.COM | 22.7 | 17.89 | 78.79 | 25
9 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16223 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bahala zone -2 PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000492/2024-2025 | 25/RD/PHE | 02/01/2025 | 16/02/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 57.51 | 0 | 0 | 0
Total | [13 empty] | 546.13 | 165.42 | 30.29