## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16224 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 4.94 | 7.83 | 100
2 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16224 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Surangapur (Zone-I) PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001954/2023-2024 | 4003278961 | 06/12/2023 | 05/03/2024 | W.B.S.E.D.C.LTD | 3.51 | 3.51 | 100 | 100
3 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16224 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Surangapur (Zone-I) PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001955/2023-2024 | 4003279009 | 06/12/2023 | 05/03/2024 | W.B.S.E.D.C.LTD | 3.39 | 3.39 | 100 | 100
4 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16224 | New | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 1681/RD/PHE | 19/06/2023 | 19/06/2023 | Resource Division | 29.81 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16224 | New | Hiring of Inspection Vehicle for office of the Assistant engineer, Raiganj Sub-Division, P.H.E. Dte. for the period from 16.02.2023 to 15.03.2023. |  |  | BILL/00945/2023-2024 |  | 05/12/2023 | 05/12/2023 | DEBASISH GHOSH | 0.32 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16224 | New |  |  |  | BILL/00989/2023-2024 | BP-2023-24-212 | 07/12/2023 | 07/12/2023 | DEBASISH GHOSH | 0.32 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16224 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Surangapur Zone- I Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018409) | Assistant Engineer - I | Junior Engineer-07 | ORD/000697/2023-2024 | 2772/MLMD | 14/08/2023 | 01/01/2025 | THE BANERJEE CONCERN | 24.02 | 21.28 | 88.61 | 88
8 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16224 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SURANGAPUR ZONE-I PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000548/2023-2024 | 640/RD/PHE | 05/03/2024 | 01/09/2024 | UTPAL SAHA | 12.24 | 12.22 | 99.83 | 90
9 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16224 | New | Implementation of SURANGAPUR (ZONE-I) and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000495/2022-2023 | 806/RD/PHE | 21/03/2023 | 27/08/2025 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 363.11 | 268.96 | 74.07 | 60
10 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16224 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Suragapur zone I PWSS at Itahar Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000471/2024-2025 | 04/RD/PHE | 02/01/2025 | 16/02/2025 | M/S MAA TARA CONSTRUCTION | 51.54 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16224 | New | Trial Run For Surangapur Zone-I PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000684/2024-2025 | 532/RD/PHE | 12/02/2025 | 13/05/2025 | M/S MAA TARA CONSTRUCTION | 0.88 | 0 | 0 | 0
Total | [13 empty] | 552.18 | 314.3 | 56.92