## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Chopra | Raiganj Division | NARAYANPUR Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | SM/16225 | New | Material Requisition To Resource Division |  |  | RTOR000140/2022-2023 | 807/RD/PHE | 21/03/2023 | 21/03/2023 | Resource Division | 27.45 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Chopra | Raiganj Division | NARAYANPUR Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | SM/16225 | New | Implementation of NARAYANPUR and its adjoining mouzas Pipe Water Supply Scheme at CHOPRA Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000034/2023-2024 | 1500/RD/PHE | 19/05/2023 | 05/09/2025 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 270.42 | 87.2 | 32.25 | 60
3 | UTTAR DINAJPUR | Chopra | Raiganj Division | NARAYANPUR Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | SM/16225 | New | Laying of Additional Pipeline with land development for NARAYANPUR Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte. under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000387/2024-2025 | 3557/RD/PHE | 05/12/2024 | 19/01/2025 | SANDIP SARKAR | 27.06 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Chopra | Raiganj Division | NARAYANPUR Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | SM/16225 | New | Construction of concrete pathway for NARAYANPUR Piped Water Supply Scheme at Head Work Site Pump House & 2nd Pump House Site under Islampur Sub-Division PHED under Raiganj Division, PHED.,U/D. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000377/2025-2026 | 2297/RD/PHE | 18/08/2025 | 16/12/2025 | WEST DINAJPUR TAPASILI LABOUR CO-OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 9.87 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Chopra | Malda Mechanical | NARAYANPUR Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | SM/16225 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Narayanpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018406) | Assistant Engineer - I | Junior Engineer-02 | ORD/000590/2023-2024 | 2639/MLMD | 10/08/2023 | 28/12/2025 | JAL PRAVAHIKA PVT. LTD. | 26.28 | 0 | 0 | 0
Total | [13 empty] | 361.08 | 87.2 | 24.15