## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/16226 | New | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 1203/RD/PHE | 28/04/2023 | 28/04/2023 | Resource Division | 22.84 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/16226 | New | Laying of Additional pipeline with other ancillary works at different mouzas of BARDAHI PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000376/2024-2025 | 3495/RD/PHE | 02/12/2024 | 16/01/2025 | APEX ENTERPRISES | 24.82 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/16226 | New | Construction of Approach Road at Head Work Site, & 2nd Tube-Well Site under New Scheme of Bardahi PWSS at Karandighi Block under Raiganj Division, PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000163/2024-2025 | 2897/RD/PHE | 25/09/2024 | 15/10/2024 | SANDIP SARKAR | 6.83 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/16226 | New | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 13.09.2024 and 18.09.2024. |  |  | BILL/00385/2024-2025 | BP-2024-25-225 | 04/10/2024 | 04/10/2024 | SAHA CONSTRUCTION | 0.05 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/16226 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Bardahi Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017556) | Assistant Engineer - I | Junior Engineer-02 | ORD/000626/2023-2024 | 2732/MLMD | 14/08/2023 | 28/12/2025 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 24.37 | 0 | 0 | 42
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/16226 | New | Implementation of BARDAHI and its adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000375/2023-2024 | 2628/RD/PHE | 13/09/2023 | 19/02/2026 | A D ENTERPRISE | 183.7 | 0 | 0 | 55
7 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/16226 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BARDAHI PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000554/2023-2024 | 654/RD/PHE | 05/03/2024 | 18/01/2025 | UJJAL KUMAR SARKAR PARTNER KUMARUJJAL51@GMAIL.COM | 11.27 | 0 | 0 | 100
8 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/16226 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BARDAHI PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000555/2023-2024 | 655/RD/PHE | 05/03/2024 | 18/01/2025 | PANDIT CONSTRUCTION PANDIT.RNJ@GMAIL.COM | 11.27 | 0 | 0 | 100
Total | [13 empty] | 285.17 | 0 | 0