## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | KOTGRAM Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/16227 | New | Implementation of KOTGRAM andit's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000010/2023-2024 | 1272/RD/PHE | 08/05/2023 | 01/01/2026 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 480.8 | 0 | 0 | 12
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | KOTGRAM Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/16227 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Kotgram Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018271) | Assistant Engineer - I | Junior Engineer-07 | ORD/000684/2023-2024 | 2759/MLMD | 14/08/2023 | 10/02/2024 | M/S MANABESH ROY | 25 | 14.77 | 59.09 | 59
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | KOTGRAM Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/16227 | New | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 2232/RD/PHE | 02/08/2023 | 02/08/2023 | Resource Division | 43.48 | 0 | 0 | 0
Total | [13 empty] | 549.28 | 14.77 | 2.69