## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Chopra | Raiganj Division | CHITALGHATA Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | SM/16228 | New | Implementation of Chitalghata and it's adjoining mouzas Pipe Water Supply Scheme at CHOPRA Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer,Junior Engineer, ISD | ORD/000047/2023-2024 | 1553/RD/PHE | 26/05/2023 | 10/05/2026 | UTTAM SAHA | 665.31 | 260.8 | 39.2 | 65
2 | UTTAR DINAJPUR | Chopra | Malda Mechanical | CHITALGHATA Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | SM/16228 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chitalghata Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018400) | Assistant Engineer - I | Junior Engineer-02 | ORD/000592/2023-2024 | 2641/MLMD | 10/08/2023 | 28/12/2025 | MANIK CHANDRA SAHA. | 29.53 | 22.52 | 76.24 | 73
3 | UTTAR DINAJPUR | Chopra | Raiganj Division | CHITALGHATA Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | SM/16228 | New | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 1053/RD/PHE | 06/04/2023 | 06/04/2023 | Resource Division | 47.89 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Chopra | Raiganj Division | CHITALGHATA Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | SM/16228 | New | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 20.09.2024 and 23.09.2024. |  |  | BILL/00386/2024-2025 | BP-2024-25-222 | 04/10/2024 | 04/10/2024 | SAHA CONSTRUCTION | 0.06 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Chopra | Raiganj Division | CHITALGHATA Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | SM/16228 | New | Additional pipeline, Pathway, Land development and other ancillary works at Chitalghata piped water Supply Scheme Under Islampur Sub-Division under Raiganj Division, P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000367/2025-2026 | 2267/RD/PHE | 07/08/2025 | 04/04/2026 | M/S PINKI CONSTRUCTION | 24.54 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Chopra | Raiganj Division | CHITALGHATA Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | SM/16228 | New | Laying additional pipe line with ancillary works for New Scheme Of Chitalghata Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division, P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000255/2025-2026 | 1488/RD/PHE | 04/06/2025 | 19/07/2025 | M/S LUCKY CONSTRUCTION | 37.92 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Chopra | Malda Mechanical | CHITALGHATA Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | SM/16228 | New | Quotation for new service connection at CHITALGHATA PH-II (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/16228). |  |  | BILL/00215/2025-2026 | 123/WBSEDCL | 08/08/2025 | 08/08/2025 | W.B.S.E.D.C.LTD | 7.15 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Chopra | Malda Mechanical | CHITALGHATA Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | SM/16228 | New | Quotation for new service connection at CHITALGHATA PH-I (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/16228). |  |  | BILL/02763/2024-2025 | BP-2024-25-627 | 06/02/2025 | 06/02/2025 | W.B.S.E.D.C.LTD | 8.1 | 0 | 0 | 0
Total | [13 empty] | 820.5 | 283.32 | 34.53