## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. | SM/16229 | New | Material Requisition To Resource Division |  |  | RTOR000144/2022-2023 | 839/RD/PHE | 23/03/2023 | 23/03/2023 | Resource Division | 31.09 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. | SM/16229 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Prraul Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018405) | Assistant Engineer - I | Junior Engineer-02 | ORD/000588/2023-2024 | 2637/MLMD | 10/08/2023 | 27/03/2026 | M/S D.G.B. ENTERPRISE. | 25.52 | 15.97 | 62.58 | 63
3 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. | SM/16229 | New | Construction Of Approach Road Of Prraul PWSS at Goalpukhur-II Block under Raiganj Division,PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000358/2024-2025 | 3306/RD/PHE | 20/11/2024 | 20/12/2024 | M/S TRIBENI CONSTRUCTION | 6.2 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. | SM/16229 | New | Earth Filling at Parrul PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000352/2024-2025 | 3305/RD/PHE | 20/11/2024 | 20/12/2024 | S.G. CONSTRUCTION | 11.3 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. | SM/16229 | New | Quotation for new service connection at PRRAUL PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00238/2024-2025 | BP-2024-25-77 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 4.69 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. | SM/16229 | New | Quotation for new service connection at PRRAUL PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00239/2024-2025 | BP-2024-25-78 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 16.25 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. | SM/16229 | New | Implementation of PRRAUL and its adjoining mouzas Pipe Water Supply Scheme at GOALPOKHAR-II Block of Uttar Dinajpur District under Raiganj Division, PHEDte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000228/2023-2024 | 2407/RD/PHE | 17/08/2023 | 01/04/2025 | S.G. CONSTRUCTION | 236.76 | 113.3 | 47.85 | 95
8 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. | SM/16229 | New | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59 D0577) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 05/10/2024 to 14/01/2025. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000357/2024-2025 | 3041/RD/PHE | 03/10/2024 | 13/01/2025 | SISIR KUMAR DUTTA | 1.35 | 0 | 0 | 0
Total | [13 empty] | 333.17 | 129.27 | 38.8