## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/16258 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 0 | 0 | 100
2 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/16258 | New | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 2242/RD/PHE | 02/08/2023 | 02/08/2023 | Resource Division | 44.72 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/16258 | New | Implementation of CHAINAGAR and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000397/2022-2023 | 749/RD/PHE | 16/03/2023 | 09/01/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 358.48 | 0 | 0 | 58
4 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/16258 | New | Arrangement for erection of display board for different piped water supply schemes (1.Jagadishpur PWSS, 2.Chainagar PWSS, 3.Hemtabad Zone-II PWSS) under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. |  |  | BILL/00436/2024-2025 | BP-2024-25-254 | 07/10/2024 | 07/10/2024 | M/S MANDAL ENTERPRISE | 0.1 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/16258 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.I of Chainagar PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02574/2023-2024 | BP-2023-24-466 | 26/01/2024 | 26/01/2024 | W.B.S.E.D.C.LTD | 4.62 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/16258 | New | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS |  |  | BILL/01216/2023-2024 | BP-2024-25-25 | 24/04/2024 | 24/04/2024 | EXECUTIVE ENGINEER PWD ROADS | 11.85 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/16258 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.II of Chainagar PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02575/2023-2024 | BP-2023-24-467 | 26/01/2024 | 26/01/2024 | W.B.S.E.D.C.LTD | 3.94 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/16258 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite at T/W no. I of Chainagar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017839) | Assistant Engineer - I | Junior Engineer-07 | ORD/000463/2023-2024 | 2481/MLMD | 04/08/2023 | 01/03/2025 | MUKHERJEE ART CENTRE | 25.2 | 0 | 0 | 85
9 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/16258 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAINAGAR PWSS at HEMTABAD Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000563/2023-2024 | 545/RD/PHE | 05/03/2024 | 19/04/2024 | MAA MANASHA ENGINEERS | 11.28 | 0 | 0 | 100
10 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/16258 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chainagar PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000432/2024-2025 | 3745/RD/PHE | 18/12/2024 | 02/05/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 46.37 | 0 | 0 | 0
Total | [13 empty] | 569.6 | 0 | 0