## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | BANGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-I UNDER UTTAR DINAJPUR DISTRICT. | SM/16471 | New | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 2270/RD | 03/08/2023 | 03/08/2023 | Resource Division | 23.83 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | BANGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-I UNDER UTTAR DINAJPUR DISTRICT. | SM/16471 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bangaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015388) | Assistant Engineer - I | Junior Engineer-02 | ORD/000449/2023-2024 | 2475/MLMD | 04/08/2023 | 29/09/2025 | DILIP MAHATO. | 26.3 | 0 | 0 | 72
3 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | BANGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-I UNDER UTTAR DINAJPUR DISTRICT. | SM/16471 | New | Construction Of OHR at Bangaon Pipe Water Supply Scheme at Goalpokhar-I Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000332/2024-2025 | 3288/RD/PHE | 20/11/2024 | 04/01/2025 | VISCOUS ENGINEERS PVT. LTD. | 71.86 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | BANGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-I UNDER UTTAR DINAJPUR DISTRICT. | SM/16471 | New | Additional pipeline, Pathway, Land development and other ancillary works at Bangaon piped water Supply Scheme Under Islampur Sub-Division under Raiganj Division, P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000370/2025-2026 | 2273/RD/PHE | 08/08/2025 | 06/12/2025 | RAHUL ENTERPRISE RNJRAHULENTERPRISE@GMAIL.COM | 45.83 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | BANGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-I UNDER UTTAR DINAJPUR DISTRICT. | SM/16471 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 16 nos. Piped water supply Schemes within GOALPOKHAR-I Dev. Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000373/2023-2024 | 2568/RD/PHE | 01/09/2023 | 14/11/2025 | ROY ENGINEERS. (PATNA) | 6530.5 | 0 | 0 | 38
Total | [13 empty] | 6698.31 | 0 | 0