## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | DAKSHIN NEAMATPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16491 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dakshin Neamatpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015935) | Assistant Engineer - I | Junior Engineer-02 | ORD/000485/2023-2024 | 2491/MLMD | 04/08/2023 | 27/05/2026 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 26.45 | 19.13 | 72.31 | 72
2 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | DAKSHIN NEAMATPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16491 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 26/08/2026 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 108.16 | 0.84 | 35
3 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | DAKSHIN NEAMATPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16491 | New | Material Requisition To Resource Division |  |  | RTOR000145/2022-2023 | 838/RD/PHE | 23/03/2023 | 23/03/2023 | Resource Division | 41.51 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | DAKSHIN NEAMATPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16491 | New | Quotation for new service connection at DAKSHIN NEAMATPUR PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/16491) |  |  | BILL/01088/2024-2025 | BP-2024-25-263 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 5.41 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | DAKSHIN NEAMATPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16491 | New | Quotation for new service connection at DAKSHIN NEAMATPUR PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/16491) |  |  | BILL/01089/2024-2025 | BP-2024-25-264 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 5.41 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | DAKSHIN NEAMATPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16491 | New | Additional pipeline and other ancillary works at Dakshin Neamatpur piped water Supply Scheme Under Islampur Sub -Division under Raiganj Division,P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000407/2025-2026 | 2366/RD/PHE | 26/08/2025 | 10/10/2025 | MILAN GHOSH | 32.18 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | DAKSHIN NEAMATPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16491 | New | Additional Quotation for new service connection at DAKSHIN NEAMATPUR PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/16491) |  |  | BILL/03208/2024-2025 |  | 20/01/2025 | 20/01/2025 | W.B.S.E.D.C.LTD | 12.62 | 0 | 0 | 0
Total | [13 empty] | 13054.65 | 127.29 | 0.98