## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16493 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 26/08/2026 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 183.69 | 1.42 | 35
2 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16493 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Samaspur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016128) | Assistant Engineer - I | Junior Engineer-02 | ORD/000440/2023-2024 | 2451/MLMD | 04/08/2023 | 09/10/2025 | ANIMA ENTERPRISE | 28.12 | 22.26 | 79.16 | 100
3 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16493 | New | Material Requisition To Resource Division |  |  | RTOR000164/2022-2023 | 962/RD/PHE | 29/03/2023 | 29/03/2023 | Resource Division | 31.81 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16493 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Vehicle no.WB 59C 4762) having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office ofthe Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entireRaiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 01/07/2024 to 14/01/2025. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Estimator | ORD/000408/2024-2025 | 1981/RD/PHE | 29/06/2024 | 13/01/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 2.6 | 0.39 | 14.95 | 100
5 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16493 | New | Quotation for new service connection at Samaspur TW-I. |  |  | BILL/03525/2023-2024 | BP-2023-24-545 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 18.97 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16493 | New | Trial Run For Samaspur PWSS under Goalpukhur-II Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000722/2024-2025 | 554/RD/PHE | 12/02/2025 | 13/05/2025 | SANDIP SARKAR | 0.87 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16493 | New | Additional pipeline and other ancillary works at Samaspur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000396/2025-2026 | 2336/RD/PHE | 22/08/2025 | 06/10/2025 | MILAN GHOSH | 46.96 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16493 | New | Quotation for new service connection at SAMASPUR PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/16493) |  |  | BILL/03654/2024-2025 | BP-2024-25-751 | 28/03/2025 | 28/03/2025 | W.B.S.E.D.C.LTD | 4.43 | 0 | 0 | 0
Total | [13 empty] | 13064.83 | 206.34 | 1.58