## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16494 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer RSD |  | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 04/10/2022 | RADIANT | 47.87 | 5.41 | 11.3 | 100
2 | UTTAR DINAJPUR | Itahar | Raiganj Division | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16494 | New | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 1694/RD/PHE | 22/06/2023 | 22/06/2023 | Resource Division | 29.47 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Itahar | Malda Mechanical | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16494 | New | Quotation for new service connection at Para PH-I (Itahar ccc) |  |  | BILL/03518/2023-2024 | BP-2023-24-538 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 3.37 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Itahar | Raiganj Division | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16494 | New | Demand for placing necessary fund for the work Permanent restoration of damaged hard shoulder/flank of L032-GULANDAR TO MUKUNDAPUR Road (Package No. WB15311 : Under DLP) caused due to pipe laying by PHED under Para PWSS at different stretched of road under WBSRDA Uttar Dinajpur Division. |  |  | BILL/00473/2024-2025 | BP-2024-25-274 | 08/10/2024 | 08/10/2024 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 1.38 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Itahar | Malda Mechanical | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16494 | New | Quotation for new service connection at Para PH-II (Itahar ccc) |  |  | BILL/03517/2023-2024 | BP-2023-24-537 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 4.11 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Itahar | Raiganj Division | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16494 | New | Implementation of PARA and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000396/2022-2023 | 748/RD/PHE | 16/03/2023 | 16/05/2026 | SANYAL ENTERPRISE | 388.91 | 138.71 | 35.67 | 52
7 | UTTAR DINAJPUR | Itahar | Raiganj Division | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16494 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Para PWSS at Itahar Block under Raiganj Division, PHE Dte.,Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000421/2024-2025 | 3733/RD/PHE | 18/12/2024 | 31/07/2025 | SANYAL ENTERPRISE | 23.02 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Itahar | Raiganj Division | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16494 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Para Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 50 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000268/2025-2026 | 1656/RD/PHE | 23/06/2025 | 20/12/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 20.73 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Itahar | Raiganj Division | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16494 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under PARA PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000494/2023-2024 | 614/RD/PHE | 05/03/2024 | 17/08/2024 | M/S MAA BAIRA KALI CONSTRUCTION | 24.47 | 0 | 0 | 100
10 | UTTAR DINAJPUR | Itahar | Malda Mechanical | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16494 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no- I,II & Making compound yard lighting arrangement at T/W no- I of PARA Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016133) | Assistant Engineer - I | Junior Engineer-02 | ORD/000434/2023-2024 | 2449/MLMD | 04/08/2023 | 26/06/2026 | SANJIB SAHA | 25.26 | 12.85 | 50.89 | 85
11 | UTTAR DINAJPUR | Itahar | Raiganj Division | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16494 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Sheme in different Block in the District of Uttar Dinajpur under Raiganj Division,PHE Dte.. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000518/2024-2025 | 58/RD/PHE | 03/01/2025 | 12/02/2026 | TECHVISION | 5 | 0 | 0 | 83
Total | [13 empty] | 573.57 | 156.97 | 27.37