## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16505 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 0.81 | 1.28 | 100
2 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16505 | New | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 1313/RD/PHE | 12/05/2023 | 12/05/2023 | Resource Division | 3.19 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16505 | New | Providing Balance Functional House Hold Connection (FHTC) For Balufara Zone-II Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000062/2024-2025 | 2225/RD/PHE | 23/07/2024 | 22/08/2024 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 6.52 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16505 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I of Balufara (Zone-II) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016905) | Assistant Engineer - I | Junior Engineer-07 | ORD/000403/2023-2024 | 2460/MLMD | 04/08/2023 | 02/12/2023 | JOY MAA SANTOSHI ENTERPRISE. | 7.18 | 7.13 | 99.3 | 100
5 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16505 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Balufara, (Zone-II), Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02582/2023-2024 | BP-2023-24-474 | 26/01/2024 | 26/01/2024 | W.B.S.E.D.C.LTD | 0.14 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16505 | New | Trial Run For Balufara Zone-II PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000731/2024-2025 | 530/RD/PHE | 12/02/2025 | 13/05/2025 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 0.82 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16505 | New | Construction of Boundary Wall With Gate at Head Work Tube-Well Site under BALUFARA ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000500/2023-2024 | 620/RD/PHE | 05/03/2024 | 16/10/2024 | M/S MAA BOLLA CONSTRUCTION | 5.56 | 0 | 0 | 100
Total | [13 empty] | 86.44 | 7.94 | 9.18