## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/16536 | New | Preparation & Submission of DPR for Proposed Bagela Piped Water Supply Scheme under Karandighi Development Block (sl no-I). | Assistant Engineer ISD |  | ORD/000807/2021-2022 | 603/RD/PHE | 15/03/2022 | 22/03/2022 | M/S SOBHA & CO. | 8.6 | 8.6 | 100 | 0
2 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/16536 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Bagela,Dalkhola C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000642/2023-2024 | 4003196575 | 20/07/2023 | 18/10/2023 | W.B.S.E.D.C.LTD | 8.06 | 8.06 | 100 | 100
3 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/16536 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Bagela,Dalkhola C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000643/2023-2024 | 4003196562 | 20/07/2023 | 18/10/2023 | W.B.S.E.D.C.LTD | 6.84 | 6.84 | 100 | 100
4 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/16536 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Bagela,Dalkhola C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000644/2023-2024 | 4003196566 | 20/07/2023 | 18/10/2023 | W.B.S.E.D.C.LTD | 3.57 | 3.57 | 100 | 100
5 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/16536 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. IV of Bagela,Dalkhola C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000646/2023-2024 | 4003196570 | 20/07/2023 | 18/10/2023 | W.B.S.E.D.C.LTD | 6.94 | 6.94 | 100 | 100
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/16536 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 1219/RD/PHE | 02/05/2023 | 02/05/2023 | Resource Division | 258.85 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/16536 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd, 3rd & 4th Tube-Well Site under BAGELA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000540/2023-2024 | 602/RD/PHE | 05/03/2024 | 19/04/2024 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 16.43 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/16536 | New | Laying of Additional Pipeline, Pathway and Land development with anciliary works for installation of FHTC Work for BAGELA Water Supply Scheme under Islampur Sub-Division P.H.E. Dte.under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000459/2024-2025 | 3777/RD/PHE | 19/12/2024 | 02/02/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 59.67 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/16536 | New | Additional quotation for HT cable at BAGELA PH-I (Dalkhola ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/03731/2023-2024 | BP-2023-24-696 | 15/03/2024 | 15/03/2024 | W.B.S.E.D.C.LTD | 14.8 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/16536 | New | Implementation of BAGELA andit's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000002/2023-2024 | 1068/RD/PHE | 11/04/2023 | 11/04/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 647.26 | 181.5 | 28.04 | 75
11 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/16536 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II,III,IV & V and making compound lighting arrangement ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Bagela Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015098) | Assistant Engineer - I | Junior Engineer-02 | ORD/000613/2023-2024 | 2726/MLMD | 14/08/2023 | 08/02/2029 | GHOSH BROTHERS... | 68.76 | 48.99 | 71.25 | 79
12 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/16536 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd, 3rd & 4th Tube-Well Site under BAGELA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000539/2023-2024 | 601/RD/PHE | 05/03/2024 | 21/07/2024 | M/S HINDUSTHAN CONSTRUCTION HCONSTRUCTION.RNJ@GMAIL.COM | 16.43 | 0 | 0 | 0
13 | UTTAR DINAJPUR | Karandighi | Raiganj Division | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/16536 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bagela Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 150 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000330/2025-2026 | 2483/RD/PHE | 12/09/2025 | 11/03/2026 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 51.99 | 0 | 0 | 0
Total | [13 empty] | 1168.19 | 264.5 | 22.64